## objectives
to increase the number of diagnostic test takers and also to increace efficiency in grading their test scores
have access for candidates who are not able to come physically to jrooz branches forthe diagnostic test

## Sheet2
Priority | features / function | def. of done | tasks | hours | assigned to | remarks
1 | integrated to jrooz - ielts online | - accessible 24/7 - link from jrooz | system installation | 4 hours fulltime | Robert | where to host?
2 | non enrolled users | - non enrolled users - could use a passcode ( system generated) - passcode will be provided by Skycare personnel | create script for passcode validation. One time use only. | 4 hours fulltime | Robert
3 | almost same module as ielts | - all Academic materials from ielts online | setup the pdf materials in a directory | 2 hours fulltime | Robert
4 | 1 hr. limit per listening, reading and writing set | - speaking not included | create a timer script | 24 hours fulltime | Robert
5 | 5 sets (Listening, Reading and Writing) Diagnostic Test, The speaking is done over the phone | - random test - 40 questions per set | create script that will randomize the 5 sets of test and save session to database | 24 hours fulltime | Robert
7 | administrator login | - login | create login script | 2 hours fulltime | Robert
8 | security / user authentication | - logout '- update password | create logout script | 3 hour fulltime | Robert
9 | tests and answer keys | - display all tests and answer keys | create script that will display the tests and answer keys | 4 hours fulltime | Robert
10 | examinees and tests information | - display examinees and their tests information | create script that will display examinees information including their exams | 4 hours fulltime | Robert
11 | track current examinee | - track the location, passcode used of the current examinee | create script that will track the location and passcode used of the current examinee | 8 hours fulltime | Robert
12 | passcode generator | - generate Passcode by admin - expire within 24 hrs. | create generate password script | 2 hours fulltime | Robert
13 | connection detection | system can tag if there are connection issue during the session | add function | 4 hours fulltime | Robert
14 | validate if the current student are really taking the exam | - add disclaimer |  |  |  | for confirmation, as per Sir John, the use of webcam
total dev hours: 85 hours
testing: 52 hours
effective hours per day is 5 to 6 hours (considering other tasks / request)
Estimated in days: 22 working days